# AInchors Nexus Platform — Cost Forecast

Generated: 2026-05-15 19:39 AEST | Day 21 | Interim: kimi active

# Executive Summary

Total spent to date: $4,179.46
Average daily burn: $199.02 (Sonnet primary)
Claude API status: UNREACHABLE (HTTP 502) — interim models active (kimi)
Daily cap: $450 (temp, reverts to $150 Sun 17 May)
OC2 ETA: Jul 6–13, 2026 (commission ~Jul 27)

# Scenario Comparison

All scenarios include 15% buffer per phase. Overall contingency varies.

| Scenario | Total | Contingency | Assumptions |
| --- | --- | --- | --- |
| A (Best Case) | $61,270 | 0% | Everything right. Claude stable. OC2 on time. No scope creep. |
| B (Realistic) | $70,460 | 15% | Claude intermittent. OC2 ~2wks late. Moderate creep. |
| C (Worst Case) | $79,651 | 30% | Claude down weeks. OC2 1mo+ late. Major creep. |

# Phase Breakdown (with 15% buffer)

| Phase | Duration | Base | +15% Buffer | Period |
| --- | --- | --- | --- | --- |
| Already spent | 21 days | $4,179 | $4,806 | ✅ Done |
| Up to OC2 | 51 days | $10,149 | $11,671 | May 15 → Jul 6 |
| P1 — OC2 Setup | 40 days | $6,000 | $6,900 | Jul 6 → Aug 15 |
| P2 + P3 | 31 days | $6,200 | $7,130 | Aug 15 → Sep 15 |
| P4 — Enterprise | 107 days | $26,750 | $30,762 | Sep 15 → Dec 31 |

# Key Assumptions

Claude API recovers and stays available (Scenarios A & B)

OC2 Mac Mini M4 Pro 48GB arrives Jul 6–13, commission by Jul 27

P2 launch target: end-Aug 2026 (contingency: mid-Sep)

No major scope creep beyond committed sprints

Gemma4:26b on OC2 reduces cloud inference costs ~40% post-P1

Daily cap reverts to $150 after Sun 17 May (temp $450 ends)

Ollama Cloud subscription: $100/mo flat (fixed, not in variable forecast)

# Key Risks

Claude API down longer than expected: Switch to Ollama full-time. Speed drops. Timeline extends.

OC2 delayed: P1 slips. P2 cascade. Costs extend beyond forecast.

P2 complexity exceeds estimate: Daily rate exceeds $250/day. Burn rate spikes.

P4 scope undefined: Enterprise multi-tenant scope could double. Wide variance.

kimi interim extends: Lower reasoning quality. More iterations. Slower delivery.

# Recommendation

Budget against Scenario B (Realistic): $70,460. This provides 15% overall contingency for moderate delays and scope creep. If Claude remains down, the interim kimi model reduces daily burn significantly, potentially bringing actual costs closer to Scenario A.

— AInchors Nexus Platform | Confidential | 2026-05-15 —