# P1 Completion — Cost Forecast Scenarios

Generated: 2026-05-15 20:03 AEST | Day 21 | Claude API: DOWN (502)

# Executive Summary

Scope: P1 completion only (up to KL team support)
Already spent: $4,179.46
Forecast range: $6,696 – $11,234
Key variable: OC2 setup vs. KL-only access

# Scenario Comparison

All scenarios include 15% per-phase buffer. Overall contingency varies.

| Scenario | Days | Best | Realistic | Worst |
| --- | --- | --- | --- | --- |
| A: Full P1 Scope | 19.5 | $8,642 | $9,938 | $11,234 |
| B: Core Min (OC2+KL) | 13.5 | $7,268 | $8,359 | $9,449 |
| C: Bare Min (KL only) | 11.0 | $6,696 | $7,701 | $8,705 |

# Scenario A: Full P1 Scope

All committed P1 work. No scope changes. 15 items, 19.5 days.

| Item | Duration | Sprint |
| --- | --- | --- |
| Three Work Types Rule | 0.5d | Sprint 4 |
| Sources of Truth Register | 1.0d | Sprint 4 |
| Cloudflare Tunnel MVP | 0.5d | Sprint 4 |
| Postgres + 5-Tier Schema | 3.0d | Sprint 5 |
| Platform Guardrails | 2.0d | Sprint 5 |
| Cost Tracker (calculated) | 1.0d | Sprint 5 |
| Tech Stream ROI / QBR | 1.0d | Sprint 5 |
| JSON→Postgres Migration | 2.0d | Sprint 6 |
| Event Bus | 2.0d | Sprint 6 |
| RAG Pipeline | 2.0d | Sprint 7 |
| PII Scanner | 1.0d | Sprint 6 |
| Typed Contracts | 1.0d | Sprint 7 |
| OC2 Setup (commission) | 1.0d | Jul 27–Aug 15 |
| KL Team Onboarding | 1.0d | Aug |
| Cloudflare Access for KL | 0.5d | Aug |

# Scenario B: Core Minimum — OC2 + KL Team

Essential only. 11 items, 13.5 days. 4 items deferred to P2.

| Item | Duration | Sprint |
| --- | --- | --- |
| Three Work Types Rule | 0.5d | Sprint 4 |
| Sources of Truth Register | 1.0d | Sprint 4 |
| Cloudflare Tunnel MVP | 0.5d | Sprint 4 |
| Postgres + 5-Tier Schema | 3.0d | Sprint 5 |
| Cost Tracker (calculated) | 1.0d | Sprint 5 |
| Tech Stream ROI / QBR | 1.0d | Sprint 5 |
| JSON→Postgres Migration | 2.0d | Sprint 6 |
| Event Bus | 2.0d | Sprint 6 |
| OC2 Setup (commission) | 1.0d | Jul 27–Aug 15 |
| KL Team Onboarding | 1.0d | Aug |
| Cloudflare Access for KL | 0.5d | Aug |

Deferred to P2: Platform Guardrails, RAG Pipeline, PII Scanner, Typed Contracts

# Scenario C: Bare Minimum — KL Team Only

Minimal viable. 8 items, 11 days. No OC2 setup. 7 items deferred.

| Item | Duration | Sprint |
| --- | --- | --- |
| Cloudflare Tunnel MVP | 0.5d | Sprint 4 |
| Postgres + 5-Tier Schema | 3.0d | Sprint 5 |
| Cost Tracker (calculated) | 1.0d | Sprint 5 |
| Tech Stream ROI / QBR | 1.0d | Sprint 5 |
| JSON→Postgres Migration | 2.0d | Sprint 6 |
| Event Bus | 2.0d | Sprint 6 |
| KL Team Onboarding | 1.0d | Aug |
| Cloudflare Access for KL | 0.5d | Aug |

Deferred to P2: Three Work Types Rule, Sources of Truth Register, OC2 Setup, Platform Guardrails, RAG Pipeline, PII Scanner, Typed Contracts

# Key Assumptions

Claude API recovers (Scenarios A & B) or kimi interim continues (C)

OC2 arrives Jul 6–13 (A & B) or deferred (C)

KL team needs: Cloudflare Access + basic platform (all scenarios)

No major scope creep beyond committed items

15% buffer per phase applied to all scenarios

# Recommendation

Default to Scenario B (Realistic: $8,359). Provides OC2 + KL support without non-essential P1 items. If Claude remains down and budget is tight, drop to Scenario C ($7,701). Only choose Scenario A if funding is secure and timeline is fixed.

— AInchors Nexus Platform | P1 Forecast | 2026-05-15 —